## Sheet1
Log Number | Team Member | Date | Hours | Minutes | Description |  | Total Time | Hours | Minutes
1 | Kai Achen, Andrew McFerrin, John Newman, Aiden Patel, Landon Pyko | 2024-10-07 | 0 | 10 | phone call to discuss potential projects and plan brainstorming for later meeting | Aiden Patel |  | 18 | 49
2 | Kai Achen, Andrew McFerrin, John Newman, Aiden Patel, Landon Pyko | 2024-10-07 | 0 | 8 | text discussion for deciding on using godot | Andrew McFerrin |  | 17 | 19
3 | Kai Achen, Andrew McFerrin, John Newman, Aiden Patel, Landon Pyko | 2024-10-07 | 0 | 3 | decided on creating a game inspired by 'Tanks' on Wii Play | John Newman |  | 21 | 22
4 | Kai Achen, Andrew McFerrin, John Newman, Aiden Patel, Landon Pyko | 2024-10-08 | 1 | 18 | created requirements stack and agile reference stories!!! | Kai Achen |  | 9 | 56
5 | Aiden Patel | 2024-10-17 | 0 | 5 | created initial architecture document and added project synopsis | Landon Pyko |  | 10 | 47
6 | Kai Achen, John Newman, Aiden Patel, Landon Pyko | 2024-10-18 | 1 | 17 | discuss requirement artifacts
7 | Andrew McFerrin | 2024-10-18 | 0 | 10 | pop in to requirment artifacts team meeting
8 | Landon Pyko | 2024-10-19 | 1 | 0 | did my two artifacts | Total Time |  | 78 | 13
9 | Aiden Patel | 2024-10-19 | 1 | 0 | did my two artifacts
10 | Andrew McFerrin | 2024-10-19 | 2 | 30 | did artifacts 10, 12, 21
11 | John Newman, Aiden Patel, Landon Pyko | 2024-10-19 | 0 | 1 | decide to build game for PC rather than mobile or both
12 | John Newman | 2024-10-19 | 0 | 56 | Created tech stack diagram for initial architecture document, image added to document and notes-resources channel on discord. Created user stories requirement artifact for requirement 3, choose game format. Added stories to sprint 1 requirements artifacts document.
13 | Aiden Patel | 2024-10-19 | 0 | 20 | separated requirements stack and story references, added sprint numbers to the entire project
14 | Kai Achen | 2024-10-20 | 0 | 30 | Completed requirements 1 and 11, created requirements artifacts, and redid the UI-flow diagram to conform with updated game rules
15 | Andrew McFerrin | 2024-10-22 | 4 | 30 | created basic assets for game, setup github repository, and learned how to use Godot to add basic movement for player character
16 | John Newman | 2024-10-22 | 0 | 20 | add code to make turret turn towards mouse. naive, need better implementation
17 | Landon Pyko | 2024-10-22 | 0 | 5 | figure out how to get GitHub Desktop to work for Godot
18 | Landon Pyko | 2024-10-22 | 0 | 20 | started messing around with some tile set stuff to have different stages. not technically necessary for this sprint, but wanted to look at it instead of doing more coding
19 | Aiden Patel | 2024-10-22 | 2 | 15 | setup godot environment for my system and GitHub Desktop. Added documentation to the repo. Started to get familiar with godot and started some stuff with making the bullet move on a mouse click. Definitely not working still but there's an idea of something there
20 | John Newman | 2024-10-24 | 1 | 0 | Added functionality for bullets and mines. left click to bullet, right to mine. Bullets move in single direction with collision. Mines don't move. both are bullet scenes with an export var to control behavior. collision shape and texture for both are assigned during creation in player_tank script. Changed player tank model to have text on the front because I couldn't tell sometimes, Old texture is marked as tank_body(old) in assets folder. Changed how mouse pos is gotten, now from a _input function which can be used for other things, it updates a mouse_pos var which then gets called when needed.
21 | John Newman | 2024-10-24 | 1 | 15 | Added walls and obstacles, commented, trimmed code bullet.gd : Added comments, removed unneeded function, added a lifetime timer and bullet deletion when timer expires player_tank.gd : Added comments to all code, added export vars to set max number of mines and bullets to have, added vars to track current number of mines and bullets assigned to player. Added functions to decrease number of mines and bullets (Called when bullet timer expires), removed some redundant mouse_pos code that I hated. added tracking for number of bullets and mines project : forgot to mention before, renamed some physics layers for my convenience. stage.tscn : changed boundaries from collision rects to world boundaries, Added one on each side of screen. added 1 obstacle named wall, currently on the same physics layer as world boundaries. maybe fine, maybe change later for some collision reason.
22 | John Newman | 2024-10-26 | 1 | 47 | Added mine class, added ricochets to bullet instances bullet.gd: changed some code so only bullet operations happen in the class. Added ricochet logic. mine.gd: created based on bullet, moved needed functions over from bullet, TODO implement the rest of the functions player_tank.gd: added refrence to mine class to create mines from player script, changed mine logic to create mine instead of bullet, removed some excess lines of code dealt with by the mine class
23 | John Newman | 2024-10-26 | 0 | 29 | Moved files to specific folders, added some placeholder files for enemy tanks and such, added hole functionality, added walls and holes as own scenes General: moved files to new scripts and scenes folders, suggest a new method if you hate it physics_layer : changed where some things layered and masked to make holes and walls work. Create scene for : main menu, maps, enemy tanks, holes, walls
24 | Landon Pyko | 2024-10-26 | 1 | 20 | Created and did all of the artifacts for Sprint 2. I would suggest everyone take a look at it and tweak it if need be
25 | Aiden Patel | 2024-10-27 | 0 | 50 | tweaked sprint 2 artifacts a little, updated requirements stack to mark completion and break down some requirements, created worklog. Updated requirements stack and worklog are in the documents folder
26 | Kai Achen | 2024-10-27 | 0 | 30 | write up game rules
27 | Andrew McFerrin | 2024-11-04 | 1 | 30 | made basic menus to navigate between screens
28 | Landon Pyko | 2024-11-05 | 1 | 40 | Added Easy movement for the AI and changed some small QoL things like bullet size, and overall speed.
29 | John Newman | 2024-11-05 | 0 | 15 | Changed enemy tank stuff Attached timer to script using scene info instead of code. Just changed timer to use scene options instead of code options. Does the same thing
30 | John Newman | 2024-11-05 | 0 | 35 | Made new branch for testing colors, Temp Color changing Made a temp method to change the color of the player tank. Created a color rect covering the tank tecture. Made an unused detailed color rect.
31 | John Newman | 2024-11-05 | 0 | 10 | changed assets to allow for easier change of colors Changed tankbody and tankgun.png to be white instead of blue. Added code to change color using modulate instead of color things
32 | John Newman | 2024-11-05 | 0 | 47 | Added broken wall functionality broken_wall.tscn: created broken wall scene to use in creation of levels broken_wall.gd: added functionality to destroy walls by calling explosion function on it explosion.tscn: created a scene for explosions because its easier to make it operate seperately from mines in my head explosion.gd: Created code to detect what is colliding with the explosion. If it has the explosion function then call that function. destroys itself after .5 seconds stage.tscn: Added broken wall to testing stage mine.gd: added code to add explosion to world at the location of the mine when mine explodes, currently only on lifetime timeout.
33 | John Newman | 2024-11-05 | 0 | 7 | Fixed the commits going to the wrong repo
34 | Landon Pyko | 2024-11-06 | 1 | 10 | Implemented basic tank destruction, messed around with the scale of things on the screen. Doing this made shooting act a little wonky so might need to go back and look at it, or change how I scaled things
35 | John Newman | 2024-11-06 | 0 | 7 | Fixed the shooting direction bug Changed scale from operating on scene to operating on background to fix the bug where turret would aim in weird directions.
36 | John Newman | 2024-11-06 | 0 | 7 | Changed tank scenes to be spawn at 0,0 The tanks started offset in their own scenes by like 15,13 pixels Chagned that so they spawn at intended posisions
37 | John Newman | 2024-11-06 | 0 | 19 | Optimized stuff for level creation/ made mine have arming period broken_wall,wall,hole.tscn: Scaled down to 48x48 pixels to match arbitrary size of tilemap stage.tscn: Made level 1 from sprint requirement no 5 tilemap: Changed tilemap to use scenes instead of images so the interaction is maintained.
38 | John Newman | 2024-11-06 | 0 | 44 | Movement testing Trying to use navigation agent to make enemies move in a tank like way. Middles of testing, have to go to class
39 | John Newman | 2024-11-06 | 0 | 30 | added the rest of the code and merged the branch I was working on.
40 | John Newman | 2024-11-06 | 0 | 8 | Changed Navigation map setup so tilemap changes it Made tilemap a child of the navmap which allows it to be used as a boundary.
41 | John Newman | 2024-11-06 | 0 | 34 | Logic to make Enemy tanks shoot randomly bullet.gd: change some things to make it work enemy_tank.gd: Create shot timer to shoot at random times, make turret rotate randomly
42 | John Newman | 2024-11-06 | 0 | 1 | pushed again because code didn't save for some reason.
43 | John Newman | 2024-11-07 | 0 | 17 | Added color support for bullets/Updated navmap upon broken wall destruction broken_wall.gd: added code to rebake the nav map upon destruction of wall. bullet.gd: Create change color func, change default color to brown enemy_tank.gd: change color of enemy bullets to dark slate blue mine.gd: change destruction of mine from free() to queue_free(). No real reason
44 | Landon Pyko | 2024-11-07 | 0 | 45 | Worked on Round Win and Loss stuff. Win screen pops up when no enemy tanks left. Made it a script of the stage.tscn since every level should abide by the same rules (John if this is incorrect feel free to change it). Round Loss should work, just don't have detection for bullet on our tank working yet. Should be pretty straightforward, we just need to make sure that our bullets don't spawn in our tank. stage.tscn: Created script to detect round loss/win player.tscn: Made a group called player so I can just check has_group() on player for round loss checking roundwin.tscn and roundloss.tscn: Basically copy pasted mainmenu.tscn to create these and repurposed them. Doing the UI was making me angry. Scripts for these are empty, need to code stage changing.
45 | John Newman | 2024-11-07 | 0 | 27 | Added medium aiming functionality enemy_tank.gd: Created a shapecast to detect players, when detected, turns turret towards player pos (no support for multiple players), made tur_dir var so easy aiming can be smooth instead of instant rotation.
46 | John Newman | 2024-11-07 | 0 | 32 | Made simple predictive shots for hard mode aiming enemy_tank.gd: added a simple version of predictive shots. predict position based on speed,distance, and position of object.
47 | Aiden Patel | 2024-11-09 | 1 | 15 | Updated sprint requirements progress levels. Created sprint 3 requirements artifacts (needs review). Updated worklog. Everything can be found in the documentation folder when I push here in a minute
48 | Andrew McFerrin | 2024-11-09 | 1 | 45 | decided on more theme choices and recreated hole sprite
49 | John Newman | 2024-11-09 | 0 | 52 | Added debug script to autoload, use for testing. Added movement for hard enemies, pathfinds to a point 150 pixels away from player. enemyTank.tscn: added dummy pointer to indicate where it is pathfinding to. Helpful debugging, changed collision layer and masks. to be what is expected. debug.gd: created and added to autoload, press t to run test. Currently just rebakes the nav mesh because im testing that. enemy_tank.gd: set difficulty to hard, added support for hard movement, namely moving towards player. made hard aiming turn faster project: made enemy a global group because it kinda is?
50 | John Newman | 2024-11-09 | 0 | 45 | Added temporary mine avoidance for hard mine.tscn: added shapcast to emulate explostion radius for testing avoidance stage.tscn: changed rendering order because it was annoying enemy_tank.gd: Made test avoidance for mines. checks for mines, sets target position about 350 pixels away to avoid explosion. Sometimes gets stuck between chasing player and avoiding mine, results in hitting mine mine.gd: added dummy function to script to detect if a thing is a mine. Can't think of a better way right now.
51 | John Newman | 2024-11-09 | 2 | 3 | Added bullet avoidance for hard tanks bullet.gd: added dummy function bullet to detect bullets, still don't know a better way eneemy_tank.gd: Added constants for distance to avoid bullets and mines by. created a dangers list to keep track of bullets and mines set start coordinates to some place on screen instead of 0,0. made tank rotate faster to mitigate issues of circle driving. removed work comments, changed mine code to add to dangers list and avoid by const. added bullet option for collider to detect bullets. added logic to predict the closest bullet will come and avoid that spot by a consts (currently 75). added bullets to danger list. changed how normal hard movement works, avoiding dangers takes priority to tracking player, added function to update dangers list. removed test code from move turret
52 | Kai Achen | 2024-11-10 | 2 | 0 | created levels 1-10 and updated main menu to be default scene upon opening the game
53 | Kai Achen | 2024-11-10 | 1 | 0 | added score mechanics (temp_score and score global variables) plus dynamic displaying of scores within levels and menus
54 | Andrew McFerrin | 2024-11-10 | 2 | 45 | created a better format for options menu and added tank color customization
55 | Aiden Patel | 2024-11-10 | 0 | 32 | added support for round win screen buttons so that player can continue through levels
56 | Landon Pyko | 2024-11-10 | 0 | 30 | Allowed player to be killed by their own bullets and enemy bullets. Both constitute a round loss (which now displays properly). Added offset on bullet spawning allowing it to spawn outside of the tank so game didn’t instantly end when you shot a bullet
57 | John Newman | 2024-11-10 | 0 | 47 | Fix mine free error mine.gd: check if parent exists before calling it added bullet color support global.gd: added bullet_color global var options_menu.tscn: added bullet color picker bullet.gd: changed my_color from export to local options_menu.gd: added code to update bullet color added enemy types enemtTank.tscn: added mine_timer to place mines on an interval. enemy_tank.gd: added support for each color of tank. types listed in sprint 2 reqs, added function to change type, which updates type and color, use this in level script to update certain tanks on ready, or we change these tanks to be a new scene. added function to place mines, added code to place mines on mine_timer timeout
58 | Aiden Patel | 2024-11-10 | 0 | 45 | updated work log again. Added functionality to difficulty buttons. Added functionality to loss screen menu buttons. Fixed option menu return button. Fixed global variables so that they reset when new game starts
59 | John Newman | 2024-11-10 | 0 | 19 | Updated navmap usage Made a nav map resource for all scenes to use. Rebakes the nav_map every oppurtunity it gets, which is not ideal, find a better solution Otherwise just added nav_map as the nav map for all level scenes
60 | Aiden Patel | 2024-11-12 | 0 | 40 | created level1_pvp scene and created some duplicates of scripts with slight modifications to get the bones of PvP in
61 | Aiden Patel | 2024-11-13 | 2 | 5 | Added controller support, controls could be modified to be more intuitive. Added every PvP stage and connected it to the game with menus so that it's playable in theory. Mines still don't work since they aren't designed to collide with Player tanks by default so that still needs to be modified.
62 | John Newman | 2024-11-13 | 0 | 19 | Warning fixes Changed a few lines to deal with warnings, mainly unused deltas. enemy_tank.gd: changed code so mine isn't shadowing the function call hole.tscn: saved it or something so there wasn't a warning about loading hole.png instead of uid whatever
63 | John Newman | 2024-11-19 | 0 | 5 | Added new folder for audio files, added demo music
64 | Aiden Patel | 2024-11-20 | 0 | 30 | improve controller controls. Now steer tank left and right with left thumb stick and move forward and back with right and left triggers. Shoot with right bumper and bottom face button (X) and mine with left bumper and right face button (O). Improved aiming with controller to be global based rotation so that its logical that moving the thumb stick right points to the right of the screen, etc
65 | Aiden Patel | 2024-11-20 | 0 | 40 | Added menu navigation for keyboard and controller so that UI buttons are highlighted. Can’t actually select anything on controller rn but you can move it around at least
66 | John Newman | 2024-11-20 | 0 | 2 | Added the game music to audio folder
67 | Andrew McFerrin | 2024-11-22 | 1 | 50 | Added basic tank treads and started to create objects to decorate background
68 | Andrew McFerrin | 2024-11-22 | 0 | 40 | created some more background details for map
69 | Aiden Patel | 2024-11-23 | 1 | 0 | added audio buses and made sliders in the option menu usable
70 | Landon Pyko | 2024-11-23 | 1 | 0 | Added a couple audio files for explosion and tank destruction. Tank destruction is not playing properly for some reason. Added an audio manager so that the game music plays between scenes and doesn't reset between scenes. Created the Final Sprint Requirements Artifacts. Feel free to add more if you think it is necessary
71 | Kai Achen | 2024-11-23 | 0 | 30 | changed bullets to only ricochet twice before being destroyed (amount can be changed by changing the ricochet_bank value in the bullet.tscn script
72 | Kai Achen | 2024-11-23 | 1 | 0 | added sounds for placing mines, player shoot, enemy shoot, bullet ricochet
73 | Kai Achen | 2024-11-23 | 0 | 10 | discovered bug bullets will destroy broken walls only after ricocheting off another wall
74 | Kai Achen | 2024-11-23 | 0 | 10 | discovered bug player 1 can only shoot five bullets total in PVP mode (unable to test player 2 at the moment but presumed the same)
75 | Kai Achen | 2024-11-23 | 0 | 10 | centered game mode select menu
76 | Kai Achen | 2024-11-23 | 1 | 0 | fixed volume sliders to work and adjusted music and SFX buses to correspond to correct sliders
77 | Aiden Patel | 2024-11-24 | 2 | 0 | refined ricochet bank and fixed bugs, added music speed up with each level, added mine collision with players, added player and player collision so players can’t drive through each other
78 | John Newman | 2024-11-24 | 0 | 51 | checked for errors and suggestions to the game process.
79 | John Newman | 2024-11-24 | 0 | 10 | checked what requirements are left
80 | John Newman | 2024-11-24 | 0 | 45 | Added PVP ready screen Added pvp ready screen. Players mark ready and then wait 3 seconds, in which they can back out. Other details can be added later
81 | Aiden Patel | 2024-11-24 | 1 | 10 | added controller selecting for ready up PvP screen, added sounds for mines destroying players and walls
82 | Aiden Patel | 2024-11-24 | 0 | 25 | updated worklog
83 | Aiden Patel | 2024-11-24 | 0 | 20 | finish requirement artifacts and stack and submit
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100