## Requirements Stack
REQUIREMENTS STACK:
Requirement ID | Description | Story Points | Priority | Sprint Number | Status
1 | Choose language/game engine | 1 | 1 | 1 | Completed
2 | Learn language/game engine (if necessary) | 8 | 1 | 1 | Completed
3 | Choose game format (2D, 3D, top-down, etc) | 1 | 1 | 1 | Completed
4 | Decide Game rules (lives, rounds, turn-based or live, etc) | 1 | 1 | 1 | Completed
5 | PvP | 13 | 20 | 3
6 | Score tracking | 2 | 3 | 2 | In Progress
7 | Player functions (move, shoot, etc) | 5 | 1 | 1 | Completed
8 | NPC functions (move, shoot, etc) | 5 | 2 | 2 | Completed
9 | Easy difficulty NPC | 2 | 2 | 2 | Completed
10 | Medium difficulty NPC | 5 | 2 | 2 | Completed
11 | Hard difficulty NPC | 3 | 2 | 2 | Completed
12 | Basic code architecture (classes and inheritance structure) | 5 | 2 | 1 | Completed
13 | Bullets and Mines | 8 | 2 | 1 | Completed
14 | Game environment (floors, walls, obstacles, etc) | 13 | 2 | 1 | Completed
15 | Game map art | 2 | 3 | 2 | Completed
16 | Game map layout | 2 | 3 | 2 | Completed
17 | Start menu | 1 | 3 | 2 | Completed
18 | Options menu | 2 | 3 | 2 | Completed
19 | Game type menu (PvE or PvP) | 1 | 20 | 3
20 | PvE menu | 1 | 3 | 2 | Completed
21 | PvP menu | 3 | 20 | 3
22 | Player art | 3 | 3 | 2 | Completed
23 | NPC art | 3 | 3 | 2 | Completed
24 | Music | 3 | 10 | 3
25 | Sound effects | 5 | 10 | 3
26 | Special actions (super shot, triple shot, etc) powerups | 21 | 20 | 4
27 | Decide on theme | 2 | 1 | 1 | Completed
| Total story points estimated: | 121